Young-LIT Project

Young literary writers and illustrators

(Agreement N°. 2001-1406/001-001 CLT-CA2

Project reference N°: CLT2001/A1/IT-241-Young-LIT)

FINAL REPORT

Summary Information

Document Title

Final Report

Project Number

Agreement N°: 2001-1406/001-001 CLT-CA2

Project reference N°: CLT2001/A1/IT-241-Young-LIT

Project Title

Young-LIT Project

Project Co-ordinator:

Comune di Bologna:

Name: 	Francesca Bruni

Address:	Area Sviluppo Socio-economico - Settore Cultura – Via Oberdan, 24 –40126 Bologna, Italy

Phone & Fax Numbers: phone: 39 051 203233

fax: 39 051 268636

E-mail:	Francesca.Bruni@comune.bologna.it

Scientific Co-ordinator/Project Manager:

Name: 	Anna Maria Brandinelli/Raffaella Gentile

Address:	Biblioteca Sala Borsa – Piazza Nettuno,3 40124 / Via Zamboni, 8 40126 – Bologna, Italy

Phone & Fax Numbers: phone: +39 051 204402 / +39 051 204884

fax: +39 051 204420/ + 39 051 218825

E-mail:  AnnaMaria.Brandinelli@comune.bologna.it, Raffaella.Gentile@comune.bologna.it

Co-organisers:

Ronneby Municipality, Library and Cultural Department:

Contact person:	 Lena Brorsdotter

Address:	Kungsgatan, 35  372 37 Ronneby, Sweden

Phone & Fax Numbers: phone: +46-457-18670

fax: +46-457-18708

E-mail:	 lena.brorsdotter@ronneby.se

Bergen Municipality, Bergen Public Library:

Contact person:	 Johanne Katrine Kolderup Flaten

Address: 	Strømgaten, 6 5015 Bergen, Norway

Phone & Fax Numbers: phone: +47 55 568501

fax: +47 55 568555

E-mail: trine@bergen.folkebibl.no

Milton Keynes Council - Learning & Development Directorate, Milton Keynes Central Library

Contact person 	Chris Murray

Address: 	Saxon Court, 502 Avebury Boulevard, MK9 3HS Central Milton Keynes, United Kingdom

Phone & Fax Numbers: phone: +44 1908 253698

fax: +44 1908 253304

E-mail: Chris.Murray@Milton-Keynes.gov.uk

Participants:

Associazione Pagine

Contact person: 	Fabrizia Poluzzi

Address:	Via del Borgo di S. Pietro, 26 – 40126 Bologna, Italy

Phone & Fax Numbers: phone: +39 051 246508

fax: +39 051 246508

E-mail:	 pagine.younglit@katamail.com

INDEX

1.	Executive Summary	6

2.	Scope and objectives of the project	7

2.1.	The need behind the Young-LIT project and its relation with Culture 2000 programme objectives			7

2.2.	Relation with other projects	8

2.3.	Objectives	8

3.	Composition of the Consortium and Role of the Partners	10

3.1.	Consortium Composition	10

3.2.	Role of the Partners	14

4.	Work carried out by the Young-LIT Project per WP	15

4.1.	Introduction	15

4.2.	Description of development, progress and achievements by Workpackage	15

4.2.1.	WP00 Project Management and Co-ordination	15

4.2.2.	WP01 Project start up	17

4.2.3	WP02 Literary and editorial workshops design and start up	21

WP03 Literary and editorial workshops implemented	21

4.2.4 WP04Materials collection and website design	26

4.2.5 WP05Website implemented and project dissemination	30

5	Summary of the main results achieved	36

6	Description of major obstacles encountered and how they were overcome	38

7	Final remarks and future prosecution	39

ANNEXES

ANNEX I. Young-LIT CONSORTIUM AGREEMENT

ANNEX II. STEERING COMMITTEE MEETINGS: LISTS OF PARTICIPANTS

ANNEX III. STYLE HANDBOOK

ANNEX IV. BOOKSLISTS (iTALY/NORWAY/SWEDEN/UNITED KINGDOM)

ANNEX V DRAFT OF THE WESITE STRUCTURE

ANNEX VI. PROJECT INFORMATION BROCHURE AND FINAL EVENT PROGRAMME

ANNEX VII. NEWSPAPER AND INTERNER ARTICLES ON THE PROJECT

ANNEX VIII. COLLECTION OF YOUNG-LIT ILLUSTRATIONS (CD-Rom)

aNNEX IX. YOUNG-lit WEBSITE DEMO (CD-Rom)

# Executive Summary

This document summarises the main activities and the results of the Young-LIT project.

In particular, it focuses on:

- scopes and objectives of the project

- composition of the consortium and roles of the participants

- description of development, progress and achievements and work carried out

- results of the project compared with those expected

- description of any major obstacles encountered and how they were overcome

- actions taken to disseminate the results

- plan for future prosecution of the project

- main Internal Reports produced in the course of the project

- materials produced for the dissemination activities and articles published on the Young-LIT project

# Scope and objectives of the project

## The need behind the Young-LIT project and its relation with Culture 2000 programme objectives

The Young-LIT project has been developed within the field of literature for young people.

In particular, it was conceived as a mean aimed at promoting at making easier reading and production of literature for a particular group of readers, young people in the age range between 14 and 18 years, the so called “young adults”, trying to investigate and understand what requirements come from this particular group of readers.

In fact, in the literary editorial field, especially as far as young people's fiction is concerned, the international exchanges and translations chosen by individual publishing houses on the basis of their editorial trends, are particularly lacking for this age range between fourteen-eighteen. We are talking of a very complex readers' target, that is, at a time of identity crisis, a delicate age of transition when only specific literature can meet the needs of a person who doesn't recognise her/himself any longer in what children's literature proposes and is not yet able to cope with and fully enjoy adult editorial production.

In this context it becomes very important, therefore, to spread among teenagers the knowledge of what exists at a literary level and is particularly addressed to them. And at the same time is relevant to stimulate the publishers, through the exchange and the critical remarks of young readers, to listen to their voice, to take into account their tastes and meet their expectations.

In addition to this, the use of new technologies offers today a great opportunity. It can be considered a way of creating a network, not only at a national level but also at an European level,, between libraries, schools and young people widening the knowledge and the use of foreign languages, and making easier exchange of experiences. Internet has a huge potential for the dissemination of information and it allows the provision of information services in a more integrated form.

To achieve these objectives the Young-LIT project was submitted under the Culture 2000 Programme, the European multiannual framework programme in support of culture with the aim of spreading the knowledge of the common cultural heritage and the exploitation of a cultural environment common to all the people of Europe. In this context, it encourages co-operation between authors, all those working in the field of culture, public and private promoters, cultural networks and the cultural organisations of the Member States and other participating states, working towards the following aims:

- Promoting cultural dialogue and reciprocal knowledge of European culture and history.

- Promoting creativity and transnational diffusion of culture, as well as the mobility of artists, authors and others who work in the field of culture, and the mobility of works, giving great importance to young people, the socially disadvantaged and cultural minorities.

- Exploiting cultural diversity and developing new forms of cultural expression.

- Throughout Europe sharing and exploiting European common cultural heritage.

- Promoting intercultural dialogue and reciprocal exchanges between European and non-European cultures.

- Recognition of the economic and social role of culture in social integration and for society in general.

- Improving access and participation in European culture for the largest possible number of citizens.

The project was submitted under the Call for proposal for the year 2001, within the initiatives in favour of European artistic and literary creation, and the experimental, innovative or specific projects type of actions:

The workarea of the Call which was covered by the Young-LIT project was the one focused on financing co-operation projects with the aim of associating authors, cultural operators and institutions operating in the literature field within reading and writing promotion projects.

The project, submitted for the April deadline, was a success for the city of Bologna that was one of the 2000 European Capital of Culture and always pays a great attention to cultural events, activities and everything linked with culture. One of the reason for the positive evaluation of the project was due to the fact that a high number of the Culture 2000 Programme objectives were included in the Young-LIT project. Among these: the promotion of cultural dialogue and the mutual knowledge of culture; the promotion of cultural creativity and transnational diffusion of culture; the mobility of artists, authors and others who work in the field of culture, and of works and giving great importance to young people, the socially disadvantaged and cultural minorities; throughout Europe sharing and exploiting European common cultural heritage; promoting intercultural dialogue and reciprocal exchanges between European and non-European cultures; improving access and participation in European culture for the largest possible number of citizens.

Not less important for the European Commission evaluation were also the Call 2001 priorities that gave particular and special attention to projects addressed to young people making easier their social integration, projects linking artistic cultural and scientific value with accessibility for a wide public and promoting the use of new technologies. All priorities met by the Young-LIT project, included within its objectives and achieved through the planned activities: support the dialogue between young people, as well as communication among youth, foster discussion and exchange of ideas between libraries, teachers, students, publishers, etc., create an on-line magazine with an emphasis on the presentation of multimedia materials created by young people, exploit the self-promotion of young people, underlining their creativity in the field of writing, drawing and the use of new technologies.

## Relation with other projects

The idea to submit the Young-LIT project has been set up in order to build on the experience and add new features (promoting reading and writing activities, contacts with authors, publishers and libraries and the creative skills of a particular target audience, usually excluded or only slightly involved by the literacy initiatives up to now undertaken) and give a European dimension to the so-called "La biglia di vetro" local initiative, addressed to children and young people of a different age range: students of primary and middle schools. "La biglia di vetro", or the "Glass marble" initiative, started in 1999, was conceived with the aim of creating an editorial group based within a large multimedia library such as the Sala Borsa, to be in permanent contact with local schools and together with them to create two magazines - one traditional and one on-line - written and illustrated entirely by school children from all over Italy.

The magazine was created by the Cultural Association Pagine, based in Bologna, its main aim is the promotion of books and the spread of love for reading. This new and important initiative was helped, in its initial phase, by the essential contribution of the Bologna 2000 Committee, that within the activities linked to its role of European City of Culture, chose and supported this idea to give the young an opportunity to be heard and to enter, as protagonist, in the increasingly widespread debate on reading and writing education.

The initiative was greeted with enthusiasm both by the schools and by the specialised press. Local primary and middle schools have been working on the project, and so have art schools (local and from other regions) and the university. So far four editions of the traditional format of the magazine have come out, because it’s published two times per year at the end of each school four months. The on-line version of the magazine has also been set up and can be seen at the following address: www.kwscuola.kataweb.it in the section “leggere e scrivere” click on the logo “La biglia di vetro on-line”.

With the Young-Lit project the target was moved to young people in a different age range, 14-18 years old, the so called “young adults”. The idea is an online literary magazine written by young people between the ages of 14 and 18 and illustrated by students attending fine arts schools in the four European countries. So this time the mean chosen was not a traditional magazine on paper, but an on-line magazine for the presentation of materials created directly by young people, easy to read and accessible both at school and at home. In fact, use of the Internet is cheaper than a printed magazine, and it makes weekly updating possible and it’s easier to catch up with pupils directly in their houses, giving them a chance to acquire editorial skills that their teachers don’t have and so don’t teach them.

As for the other partners, most of them have already had experiences and project focused on young people and sometimes also dealing with literature.

## Objectives

As stated above, in the literary editorial field, especially as far as young people's fiction is concerned, the international production chosen by individual publishing houses on the basis of their editorial trends, are particularly lacking for the age range between 14 and 18 years, the so called “young adults”. So it becomes very strong the need to spread among teenagers the knowledge of what exists at a literary level and is particularly addressed to them and at the same time stimulate the publishers, through the exchanges and the critical remarks of young readers, to listen to their voice, taking into account their tastes and meeting their expectations.

Young-LIT is a project in which four Libraries of four European cities, in collaboration with a private technical partner, decided to increase and promote reading and publishing of literature for this particular group of readers, the so called “young adults”, trying to investigate and understand what requirements come from them through the setting up of editorial workshops and the use of common ICT based tools.

Through their activity partners aimed at creating a European communication network, which, by means of the direct participation of young people, the involvement of the operators in the field, the institutions and the authors, is able to supply young adults (14/18) with an instrument that allows them to exchange information about local and national publications, in order to get to know authors from their own and other countries. The project’s aim was, in fact, promoting, through young people’s suggestions, the translation and publication of targeted titles.

To realise its objectives, Young-LIT did the following:

- (1) created four editorial workshops in four European Libraries connected with one another and with the involvement of schools, teachers and schools;

- (2) developed a Young-LIT website.

The primary goal of the editorial workshops (1) created in each country within the Young-LIT project was to establish a link with young people aged 14-18 years, schools and teachers in order to provide materials and works for a literary e-magazine designed and written by young adults available on the Young-LIT Website (2). The network of local editorial offices was co-ordinated by the project leader, Municipality of Bologna with the support of the Italian technical partner and was in the Sala Borsa Multimedia Library.

Following instructions on the website, students acted as journalist reviewing books, interviewing authors, librarians and booksellers, and creating their own list of more interesting books, even working from the library, their classes or from home, keeping in contact touch with their national editorial office. According to the partners’ intention the website should continue to be up-dated also in the future with direct contribution and involvement of young visitors becoming a reference point for young adult readers, publishers, libraries, authors and booksellers throughout Europe, widening relations with other countries, fostering discussion among students, promoting reading and creating a direct relationship with authors most loved by young people, who became on the pages of the magazine also examples of creative writing.

# Composition of the Consortium and Role of the Partners

## Consortium Composition

The Young-LIT partnership is composed in such a way as to guarantee an important balance for the coverage of the needs related to the envisaged activities and the further exploitation of the project results.

The Young-LIT project has, in fact, brought together four Municipalities (Bologna Municipality, Ronneby Municipality, Bergen Municipality and Milton Keynes Council), in particular their public libraries, and a technical partner the Cultural Association “Pagine” (Bologna), operating in 4 different countries (Italy, Norway, Sweden, UK).

The project participants are:

- Municipality of Bologna

The "Young-LIT" project was co-ordinated by the Municipality of Bologna, and in particular by the "Sala Borsa" Multimedia Library, as regards the scientific and technical co-ordination, with the support of the International Relations and Projects Office, as regards the administrative and financial co-ordination. In this way, was possible to guarantee both the quality of the project's results, its widest dissemination throughout Europe and the respect of the foreseen timetable, workplan and all contractual conditions ruling the relationship with the European Commission.

The Municipality of Bologna is among the most important and well-known municipalities of both Italy and Europe.

On November 20, 1995, the European Union's Council of Ministers of Culture named Bologna European City of Culture for the Year 2000. Since Florence in 1986, and therefore for the first time in fourteen years, Bologna is the second Italian city to be accorded such prestigious recognition—recognition that testifies to the beauty, history, and cultural vitality of the city, yet also poses new challenges: to prepare a program that showcases the importance of Italian culture, enriches the city with more opportunities for culture and the arts, and makes our city even more pleasant and welcoming.

The festivals and exhibitions put on at both a national and an international level were great opportunities for cultural exchange, which nowadays has become important focal points in the network of cultural production and participation, currently on the increase world wide. Bologna’s desire for Europe can be seen furthermore in the city’s adhesion to a number of networks of European cities within which it has always been one of the most active participants (e.g. EU NET ART, Eurocities, Telecities, Healthy Cities, etc.).

The Biblioteca multimediale Sala Borsa (Goods Exchange multimedia library) is meant to be the hub of library services in the metropolitan area of Bologna, alongside with the historical library of the Archiginnasio. It was opened to the public last year on December 2001 after the beginning of the Young-LIT project.

Today the municipality of Bologna runs 22 libraries (2 central, 9 specialized, 11 branch libraries).

The new library - which has taken over the tasks of the former Central Library - must provide a public library service to a highly educated population: among over 25’s, 37,2 % holds a high school or university degree, 1 person out of 10 has a university level knowledge. The University, the oldest in Europe, employs about 3.000 teachers and has 94.000 students, 68.000 of whom come from other counties.

The new library cater for all ages and social groups. It has a good foreign languages collection, and a new attention to the needs of immigrant groups.

Books, serials, music cd’s, videos, cd-rom are directly available to the public.

All catalogued records are on-line, and part of the metropolitan network which already connects municipal libraries, the State library and 90 libraries of the University of Bologna. This network is part of the SBN (Servizio Bibliotecario Nazionale, the nationwide library service) and is available on Internet at the homepage http://www.cib.unibo.it. On Internet is also the civic network, which can be reached at the URL http://www.comune.bologna.it (both have English versions). Thanks to this double link, libraries can therefore act both as bibliographic and community information centres.

Lending service, acquisitions, statistics are all automated.

Readers are able to use their city card for registration as readers, self service lending operations, payment of fee services. The city card is also in use for certifications, booking of health service visits, payments. The building is cabled to integrate phone and data network, security systems, TV and audio transmission.

The focus are on all information services and user’s education techniques. A special stress has been given on helping all users to become familiar with automated research programs.

The “Sala Borsa Ragazzi” library is the area were most of the material in the young people’s section of the library can be borrowed by children and young people.

Young users can consult, read, listen to and look at all the different kinds of material available in each of the rooms of the Young People’s library.

The audio-visual and multimedia material not available for borrowing can be consulted at the three reserved work stations: one in the children’s section and two in the exhibition section.

For borrowing by a class, the school class itself is usually enrolled, and in this case the class teacher is responsible for returning borrowed material by the due date.

Books can be borrowed for 30 days and multimedia documents for 7 days. School classes can borrow up to 25 books for up to 45 days.

The Sala Borsa Ragazzi PCs allow access to all local and remote resources available to the Library, apart from those work stations reserved for the consultation of the Library’s catalogues.

The site of the new library is, at the same time, rich of historical suggestions. It is situated in the center of town, in the same Palazzo d’Accursio which runs back to the XIIIth century and has always been the center of political and administrative power. It now houses the Mayor, the City Council, the Communal Collections of Art and the Museum “Giorgio Morandi”. Through windows in the pavement of the central “piazza” (1000 square metres) people can see a Roman street, the foundations of a medieval tower, a XVIth century fountain, built for the first botanical garden planted in Bologna, which occupied this area. The central part of the library, crowned by two wide galleries, was the 1883 stock exchange hall, later the collector’s office and then also used as a sports hall. With its information center, newspaper area, café and shop, it is a sort of meeting point, the place for large exhibitions and conferences. One of the corner areas used to be a very popular puppets’ theatre. That area is now dedicated to children library services.

The "Sala Borsa" was also assisted in the scientific and technical co-ordination of the Young-LIT project, as participant, by the Cultural Association "Pagine" ("Pages"), whose specific statute tasks are to stimulate reading and writing activities, especially within schools, to support teachers in carrying out specific projects dealing with reading, to provide them with tools, expertise and information, to organise training sessions and debates on these issues, to publish articles on pupils' and young people's literature. As regards the graphic design of the Young LIT Web Site, the city will involve students coming from the Istituto Rizzoli and the International Institute of Designers located in Bologna.

Facts and figures of the Sala Borsa multimedia library

| area to the public | 11.780 square metres |
| --- | --- |
| capacity: | 390 - 400.000 volumes |
| open access | 216-220.000 |
| stacks | 174-180.000 |
| books at the opening | 120.000 |
| periodicals | 320 |
| newspapers | 45 |
| opening hours | Mon. 14.30-21.30 Th.- Fr. 9-21.30 Sat. 9-19 |
| personnel | 90 persons |

- Ronneby Municipality, Library and Cultural Department

Libraries in Ronneby let local citizens' use computers fairly early. In 1989 the electronic library Infocenter, arranged in the science park Soft Center, offered opportunities to access like CD ROM and external databases. Some years later, when a fibre network linked Soft Center to a number of public premises around the town, the Infocenter, www.ronneby.se/infocenter, experiences and competence where transferred to the city's Public Library, www.ronneby.se/ronneby/biblio .

The mission then stated by the local parliament was to enable IT citizens' right and therefore to make the new technology available, including hardware, software and training activities. Already before Internet graphical interfaces where designed for access to different software and information sources. Courses were arranged informing people of the information society and its facilities. Special initiatives where taken to support retired, women and girls, sight disabled. To stimulate contact from citizens to the local parliament special forms for e-mail correspondence with individual politicians were offered to use from the libraries' computers.

In the middle of the 90th the libraries started to use web as a service to citizens. The staff was trained to know more about web, and how to produce web pages. In the libraries, including branch libraries in villages of the countryside, Internet has been available for free all time since then. Since 1999 the ordinary book catalogue of Ronnebys’ libraries have been available on the web.

At the end of the 90th IT workshops were implemented in Infocenter as well as the city's library. Special computer equipment and software were arranged for training purposes in the spirit of electronic learning. To the IT workshops were video studios connected to use for lecturing and net-based discussions. Parts of the activities have been performed in collaboration with the Blekinge Institute of Technology, www.bth.se/eng , who is a member of the Swedish Distance Learning University Group.

During year 2000 a project with funding from Statens Kulturråd , The Swedish National Council for Cultural Affairs, have taken place. One librarian has worked as a “Virtual librarian”, helping schools with library services. Performing this an application that has come true thanks to the EC-funded project EQUAL, www.ronneby.se/equal/eindex.htm .

- Bergen Public Library

Bergen has 227.000 inhabitants, and geographically it is a large town, 465 square kilometres. Some areas are densely populated while others are not.

A library in Bergen was founded as early as 1317 and so has a very long history. Bergen Offentlige Bibliotek, the present day Municipal Library was founded in 1872. Its current premises was completed in 1917 and is now a listed building.

Besides a wide range of modern Norwegian and foreign literature the library owns several older collections of great value, including the Grieg archives containing 660.000 books, magazines, newspapers, sheet music, CDs, videos etc.

All our documents (except sheet music) published since 1964 are available on the Internet, but most of our older collections are not yet available electronically.

The library currently has 7 branch libraries and a bookmobile, 4 of the branches are quite large by Norwegian standards. In addition the Norwegian state authorities pay the Bergen library to run library in a state prison in Bergen.

Following a survey of user preferences several years ago, some smaller branches were closed and the bookmobile service was intensified. This is an important supplement particularly for children and the elderly, or others who do not drive.

Since 1994 library use in Bergen has increased by more then 50%.

Children are very important to Bergen library and most of branches have a librarian with special responsibilities for children. School classes are invited to visit the library; children from the age of 3 upwards are invited for story telling and theatrical productions. Each department has a PC linked to the Internet for children to use, and even when a small branch has only one PC, this is in the children's department. Children and young people are in fact the most frequent users of the library. Although they do not necessarily borrow much they visit the library to read, listen to music, to use the PCs and the Internet and to study and do research for their school work.

In fact, from September 2001 the library has been involved in a very interesting project dealing with literature and young people (17-19 years old) called  "Poetrysense". This pilot-project was initiated by Norwegian Writers Center and fully funded by The Norwegian Culture Fund and the Ministry of Culture’s National Library Authorities. The project’s aim was to give young people the opportunity to work with contemporary poetry in a quite different and more active way than they do in the schools.

Since 1995 a development plan for the library has improved services and the IT element especially for the public. Net-library, a Bergen library on the Internet, funded by state authorities has recently been established. The different sections include a children's department., a section on Western Norwegian authors, and a section on local history and the Grieg collection.

- Milton Keynes Central Library

Milton Keynes, conveniently located midway between Birmingham and London and bounded by Bedfordshire to the north-east, Northamptonshire to the north-west and Buckinghamshire to the south and west.

Still growing by approximately 3,000 a year, it already has a population of over 190,000 and has established itself as an important regional centre. Further recognition of Milton Keynes “coming of age” is the Council’s successful bid to become a unitary authority, which took effect from 1 April 1997.

The Borough encompasses the older towns of Bletchley, Newport Pagnell, Olney, Stony Stratford, Woburn Sands and Wolverton, together with numerous villages and, of course, the city of Milton Keynes.

Milton Keynes College has three major centres in the Borough, with some 7,000 students pursuing further Education courses.

Milton Keynes is the home of the Open University and De Montfort University has established a campus in the city. The education service also has a long-standing relationship with Leicester University's School of Education and Education Management Development Unit in Northampton.

The Council's Learning and Development Directorate has overall responsibility for the education service in the area. The Directorate brings together Community and Economic Development, Education and Library Services and Children’s Social Services. Its major aim is to ensure integrated and effective services for children and young people and lifelong learning opportunities.

Libraries are an integral part of the Educational Service. The Library Service comprises 8 branch libraries and one mobile library service in the area.. HMP Woodhill also receives a service as does the local hospital. The branches fall into 3 groups in terms of size and performance. The Central Library issues over 1.3 million items per annum with Bletchley close to 400,000. Three of the other branches issue 150-200,000 with the three smallest branches issuing just over 100,000 per annum. Westcroft is the newest library (opened in 1996) and unusually is located in a shopping complex.

The Milton Keynes Central Library is the busiest library in the country and the service as a whole is wide-ranging and of very high quality. There is a well established tradition of support for schools through the School Library Service in terms of advice, availability of specialist collections of books, loans of books and materials, exhibitions, production of guides and resources lists and other information for schools. The Library Service forms part of the Learning and Development Directorate and reports to the Economy and Lifelong Learning Committee of Milton Keynes Council.

The Central Library has a total book stock of over 137,000 volumes and approximately 17,000 audiovisual items. There are currently 11 full time professional library staff running all departments.

The Children’s department is involved in various projects dealing with literacy and pre-school children.

Bookstart for babies is a national project aimed at introducing babies to books through the local Health visitors. Parents are presented with a bag that contains board books and an enrolment form for the library. This pack is given to them by the Health Visitors at the baby’s 7-month health check.  This, coupled with the regular baby storytimes, helps to introduce children to books from a very early age.

Surestart is an initiative that aims to provide literacy support to those areas of the community that have been identified as in need.  Those areas that may not be able to provide their children with books, or do not have access to learning resources, will through Surestart.

## Role of the Partners

The table below summarises the role of each Co-organisers in the project

|  | Name of the partner | Project Co-ordinator | Co-organisers | Participants |
| --- | --- | --- | --- | --- |
| 1 | Comune di Bologna – Biblioteca Sala Borsa | X |  |  |
| 2 | Ronneby municipality, Library and Cultural Department |  | X |  |
| 3 | Bergen public library |  | X |  |
| 4 | Milton Keynes central Library |  | X |  |
| 5 | Cultural association pagine |  |  | X |

The project has been managed by the International Relations and Projects Office of the Municipality of Bologna, whereas the scientific and technical co-ordination has been carried out by the Sala Borsa Library with the support of the Cultural Association “Pagine”.

As overall scientific and technical co-ordinator, the Municipality of Bologna and in particular the expert librarians of the Sala Borsa Library with the contribution of the Cultural Association “Pagine”, have been responsible for establishing the technical specifications for the partners so as to organise and co-ordinate editorial workshops in schools in Italy.

All Partners have been involved in all project phases.

# Work carried out by the Young-LIT Project per WP

## Introduction

The Young-LIT project lasted 10 months (Sept 01-July 02) and was divided into 5 Workpackages.

The table below gives a graphic representation of the duration of each WP.

| WORK PACKAGES | Sept 01 | Oct 01 | Nov 01 | Dic 01 | Jan 02 | Febr 02 | Mar 02 | Apr 02 | May 02 | Jun 02 | Jul 02 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP00 Management and Co-ordination | Bologna |  |  |  |  |  |  |  |  |  |  |
| WP01 Project start up |  |  |  |  |  |  |  |  |  |  |  |
| WP02 Literary and editorial workshops design and set up |  |  |  |  |  |  |  |  |  |  |  |
| WP03 Literary and editorial workshops implementation and working |  |  |  |  |  |  |  |  |  |  |  |
| WP04 Materials collection and Website design |  |  |  |  |  |  |  |  |  |  |  |
| WP05 Website implemented |  |  |  |  |  |  |  |  |  |  |  |

## Description of development, progress and achievements by Workpackage

### WP00 Project Management and Co-ordination

Starting date: 12-09-01 Ending date 24-07-02

#### Objectives

This Work Package was aimed at co-ordinating the whole project, defining the overall plan, keeping contact among the partners and checking the compliance of the activities with the programme and schedule and the compatibility of costs.

The WP included all project management activities, such as:

- definition of the overall plan for the project

- co-ordination and preparation of the consortium agreement

- co-ordination and organisation of the editorial workshops in each country

- organisation of periodical meetings

- monitoring progress and activities

- overall co-ordination in the preparation of the Final Report

- overall financial co-ordination and support in the preparation of cost statements

#### Approach

The general management approach concerned the implementation of the project within a framework that enabled problems to be resolved in a fast, efficient and fair manner, that ensured co-ordination of the different actions, in order to promote synergies on technical issues, to achieve economies of scale and to promote mechanisms for the effective dissemination of project results.

The lines mapped out for the efficient management of the project, adapted to the specific circumstances, included:

- a Project Steering Committee, chaired by the Bologna Municipality, comprising two representative for each city

- common procedures, tools and survey methods, reducing interface costs and allowing information to be progressively updated.

#### Main results

The work has been carried out according to the work plan presented in technical Annex I to the Agreement signed between the Municipality of Bologna and the European Commission . The main outcomes regard:

- Project management plan: after an in-depth analysis carried out at local level in which all activities were checked the working plan was officially approved at the first meeting held in Bologna on 29-30/10/01. The plan, reflecting the technical annex, defined the roles and responsibilities of the participants and professional figures involved in the project.

- Approval of the Consortium Agreement setting out the obligations of the project partners and the procedures to be followed

- Setting up of the local co-ordination team, definition of the procedures to be followed and of the activities to be carried out

During the course of the project, the following Steering Committee meetings were organised:

- Bologna, 28th, 29th and 30th October 2001, during which management and financial issues were tackled, partners agreement and project plan discussed and roles and responsibilities of the partners in the implementation of the project workplan defined

- Bergen, 25th and 26th February 2002, during which the progress of the project was discussed, particularly as regards the workshops implementation in each country, the Website technical design, the management of the Website, the criteria for the selection of the materials to be uploaded, the dissemination strategies

- Bologna, 27th and 28th May 2002 during which the main results of the project were discussed, the design of the Young-LIT Website was approved, the project Website was officially launched (27th May 2002, on the occasion of the Young-LIT public event), management and financial issues discussed and partner agreed the future continuation of the project activities.

#### Comparison of work done against plan

Some slight deviation from the original plan were made.

The first one was due to the fact that the project start up was delayed since the agreement with the Commission was signed only in September, so the first workpackage started in September instead of May 2001, leaving unchanged the other phases.

For this reason and for others related to the project activities (Web site start up phase and its implementation, date of the public final event in Bologna), an extension of one month of the eligibility period was requested and approved by the European Commission, postponing the conclusion of the project from May 24th to June 24th, without affecting the deadline of the project which remained July 24th.

The second deviation was the overall number of Steering Committee meetings. Since the project duration was very limited, partners decided to hold only three meetings and one final event instead of the five originally envisaged in the workplan, keeping in constant touch by e-mail.

### WP01 Project start up

Starting date: September 2001 ending date: October 2001

#### Objectives

The main objectives of WP1 were:

- define common guidelines and methods for the creation of the literary and editorial offices in each country located in a public library

- identify and select schools and/or students to  involve in the production of works and materials for the Young-LIT website.

- definition of a common model for the editorial handbook (Style Handbook)

- definition and discussion of a first draft of the website structure and contents.

#### Activities

Some of the project activities with schools had already started ,at least in Italy, in May 2001.

As envisaged in the Young-LIT project, the local team started by planning the activities to be carried out with schools. In order not to be caught unprepared in September at the start of the school year, in case the project was approved, they contacted a few upper secondary school literature teachers to ask them to attend a meeting. The objective was to illustrate the workshops that would be organised from October onwards, also in view of the fact that schools projects take long to get underway, as each proposal must be approved by the school board.

Then a proposal was presented for the illustration of the Young-LIT Website and it was decided how the workshops in art schools would be conducted. The matters were discussed and a general agreement was found with teachers of art institutes with whom contact had been made during the previous experience with the literary magazine for elementary and lower secondary school students, called “Biglia di Vetro” ( Glass Marble).

After the end of the school year, a first “list of possible contents” for the Website was drafted and an outline of the style manual too.

After the project was approved and the agreement with the European Commission signed, in the month of September partner countries were contacted in order to define the shared actions to carry out. Partners agreed to hold the project kick-off meeting at the end of October. But there were already some activities that needed to be started as soon as possible, before the first project meeting. So a letter was drafted with the contribution of Tiziana Nanni from the children's library of Bologna to be sent to upper secondary schools in order to provide them with the opportunity to participate in the reading and writing workshops for the Young-LIT project, and teachers previously met in May and June were contacted again.

A list of 50 titles was then drafted, selected among series published for young people, to be distributed to several classes according to age groups.

At the beginning of October a second message was sent to the partner countries stating that in Italy the distribution of the 50 titles had already started in eight upper secondary schools in a total of 10 classes. Photocopies of the front and back covers of the chosen titles were distributed to the Arts Institute of Bologna, the Academy of Bologna and the Institute of Design of Milan, in order to prepare illustrations for the books.

In order to start activities with young people in the partner countries too, the co-ordination team in Bologna prepared and delivered guidelines for the implementation of literary workshops in school and editorial offices in each country.

So each local co-ordinator started the following activities in their own countries:

- Selection of fifty titles of books among literature produced specifically for young people, or more precisely for the fourteen-eighteen age range, the so-called "young adults", by both national and foreign authors

- Checking if there were any common titles in the four countries

- Selection of three authors from each country (Italy, Great Britain, Sweden, Norway), having at least one book in translation in the other countries involved in the project. This proved rather difficult, so it was agreed that local co-ordinators could reduce the number if they thought it was is too high.

- Selection and contact with four or five classes in different schools, which had students in the follow age ranges: 14/15, 15/16, 16/17 17/18 and if possible 18/19. The school system in Sweden and Norway is different from the Italian one, but fortunately the age range for high school students is the same as in Italy (14-18).

- Set up a workshop in every class with the aim of getting students in each class to read at least ten books and then review them.

In this first phase, before the common editorial handbook was ready, local co-ordinator activities had been limited to delivering ten books to each class, asking students to read, exchange and discuss them. If a class asked for more books, this was not a problem: if the number of books read and reviewed at the end exceeded 50 for each country, the reviews would be published on the Website, adding to its content.

The other step was to select an art schools that would work on illustrations for the books reviewed by other students to complete the literary Website. Usually pupils were given only a copy of the back cover and first pages of the book because they were not interested in reading the books, but mostly in just illustrating them. For this initial phase it was enough to establish contact with art schools, without starting workshops.

After these initial activities at the end of October 2001 the project kick-off meeting (ANNEX II List of partecipants) was organised in Bologna, on 28th, 29th and 30th October 2001. Partners from Milton Keynes didn’t attend this project meeting for some prior engagements, which they weren’t unable to cancel, but of course this didn’t reflect their commitment to the Young-LIT project.

During the meeting the main issues discussed were:

- Definition of a Consortium Agreement

- Discussion of guidelines and methods for conducting literary workshops and setting up an editorial office

- definition of a common model of the editorial handbook (Style Handbook)

- definition and discussion of the draft website structure.

(1) A draft version of the Consortium agreement had been sent by e-mail before the kick-off meeting and was illustrated by a representative of the Municipality of Bologna and discussed among participants.

There weren’t any comments or suggested amendment, so Partners agreed a schedule to finalize the signature process.

(2) Partners discussed guidelines and methods for the organisation of the literary workshops and the editorial office in their country, proposing some slight changes to the common model proposed by the Italian co-ordinator in order to adapt it to their own school structure and needs.

The idea is to create a European on-line magazine written by young people between the ages of 14 and 18 and illustrated by students attending fine art schools in four European countries. The magazine should be easy to read and accessible both at school and at home. The structure proposed, in line with the Young-LIT project, is to have an editorial office in each country, located in a public library, that receives applications and project proposals from the schools or directly by students and is at the students’ disposal.

The editorial offices are based at the following address:

For Italy: “Sala Borsa” Multimedial Library, Piazza Nettuno, 3 40124 Bologna (contact person: Tiziana Nanni, telephone: +39 051 204429 or Serena Sorbi, telephone: +39 051 204483, e-mail: younglit@comune.bologna.it)

For UK: Milton Keynes Central Library, 555 Silbury Boulevard Saxon Gate East, Central Milton Keynes (contact person: Paul Dorney, telephone: +44 1908 254050, e-mail: Paul.Dorney@milton-keynes.gov.uk)

For Norway: Bergen Off. Bibliotek, Strømgaten 6, 5015 Bergen (contact person: Karen Marie Loge, telephone: +47.55.56.85.99 / +47.55.56.85.96, e-mail: karenm@bergen.folkebibl.no)

For Sweden: Library of Kallinge. Torget, 37250 Kallinge, Ronneby (contact person: Lena Mattisson, telephone: +46 457/18756 mobile phone: +46 708/186722, e-mail of contact: lena.mattisson@ronneby.se)

The organisational framework has a pyramid structure consisting in :

1) A transnational co-ordinating team based in Bologna, which coordinates, for the duration of the project, the work in all four countries by creating and updating the website.

2) An editorial office based in a library in each of the four European partner countries. Each editorial office conducts the workshops, collaborates with teachers to develop students’ professional skills, receives all the material to be published, and is responsible for the final editing of all texts.

3) Various virtual workshops spread throughout each country. Each workshop allows students, in collaboration with teachers and/or librarians, to read, gather information, acquire journalistic and editorial skills, and write pieces to be sent to their country’s editorial office. The same process applies for illustrations which are contributed by students from fine arts schools.

As for the workshops, schools, libraries or individual students interested in participating in the project initially contact their country’s editorial office to receive instructions on setting up the workshops, at least until the launch of the project website. In most cases the teachers or librarians who collaborate on the project had already been working with students for number of years in one of the designated areas: some have been passionately dedicated to teaching creative writing and have collected interesting pieces by the students; others experimented with journalistic-type work and created class newspapers written by the students.

In short, the on-line magazine simply collects the most interesting work produced in the schools and offers the possibility of an exchange between young people at European level, acting as a virtual meeting point. As regards technical aspects, they can consult the Style handbook in the first phase distributed to both teachers and students and available through the magazine.

(3) A copy of the Style handbook, draft version, was delivered to the partners.

As regards the Style Handbook, in relation to the technical aspects, the intent was to distribute it to both teachers and students involved in the project between November and December and to make it  available through the Young-LIT website after the initial distribution. The aim of the manual is to enable contributors to write a text that is correct from the publishing and editorial points of view, to provide students with editorial guidelines for composing a text, while the teachers worked with them in a more direct way depending on their areas of interest.

It is an educational tool to be used in schools. In fact given the various sections of the website, students were asked  to acquire the specific competencies of roles that are substantially different from each other, whether it is writing reviews and articles or poetry and other free, creative works, whether, in other words, they take on the role of journalist or creative writer. In any case,  the Style Handbook provided them with editorial guidelines for composing a text, while the teachers work with them in a more direct way depending on their areas of interest.

During the meeting all the partner agreed to share only the first part of the Style Handbook, and to leave the grammatical part to be written directly by each country because there are rules which are specific to each language.

Only the Norway partner decided not to have a Norwegian Style Handbook because they decided to work directly in English with their students, who are quite fluent in English .

- definition and discussion of the first draft of the website structure.

During the meeting an initial proposal for the website structure was presented and discussed with the other partners.

The idea originally proposed by the co-ordinator was to have one common international home page with general information about the Young-LIT project and one home page for each country with a replica of the main web structure for every country’s website. All sites would be linked, but each partner would be able to decide their own items.

The content proposed was to have various sections. The two main ones would contain reviews of books published specifically for “young adults” and articles on authors from each country. The sections proposed would be structured as follows:

Project presentation: brief description of the project and how it is set up.

How to take part

Style Manual: a section briefly explaining the procedures for publishing items on the site,  sending articles and illustrations, space availablility, and so on.

How to participate in the editing: how schools or individual students can take part in the editing process, how to send e-mails with txt or jpg attachments for example.

The Bookcase

Reading suggestions: list of books recommended by the editorial team to be reviewed and illustrated.

Reviews and illustrations

Collection of reviews and illustrations:  the most substantial part of the website contains reviews of fictional works. Alongside some reviews there would be also an illustration contributed by a student from an arts school representing his or her interpretation of the book in question.

Various articles

Meeting Authors: articles written by students on local authors.

Various: each issue contains articles on European literature for young people, curiosities, studies on a publisher’s series or interdisciplinary projects with the English teacher in collaboration with other student partners.

Creative writing

Personal Writing: section dedicated to those students who write poetry or stories and who see themselves a bit as writers.

Quiz and games: section dedicated to literary games, quizzes, and riddles, with prizes awarded (books, obviously!).

Archive: the website is constantly updated, but all the material can be consulted in the archive.

In the meeting all the partners agreed that one common website rather than four replicas of the main Web structure for each country would be enough, and this would give a real European dimension to the project site.

So it was proposed and accepted that it wasn’t necessary to have four different sites for each country, but only one common European site and one common database.

The use of a technological tool was proposed by the Ronneby partner to be used until the Young-LIT website would be ready. It was illustrated by Peter Blaschke, the IT expert from Ronneby city, and its features were briefly explained. The LUVIT tool (luvit.bth.se/young-lit) could be used to communicate between schools, each school would have a password and a user name. It is structured with a lot of sections, such as news, agenda, people-on-line (a forum) and could  be used as a tool for exchanging ideas and communicating both between partners and also between students. It would  become the “forum” where pupils could start  exchanging reviews and debating about books read, at least for the time being. So, initially, works would be placed on the LUVIT site, to be later transferred permanently to the Young-Lit website.

All the partners agreed that it would be a very useful communication tool to be used until the Young-LIT website was ready, registering all people working in the project and also the schools involved in editorial workshops in each country.

#### Main Results

- Definition of a Consortium agreement (see ANNEX I – Young-LIT Consortium Agreement)

- Definition of initial activities to be started in each country

- First draft of the website structure

#### Comparison of work done against plan

- No amendments were made to the original plan

### WP02 Literary and editorial workshops design and start up

### WP03 Literary and editorial workshops implemented

WP02 Starting date: October2001; Ending date: November 2001

WP03 Starting date: November2001; Ending date: January 2002

#### Introduction

The workpackages two and three are so tightly linked that it seems appropriate for the purpose of this Report, whose aim is to provide a description of  the overall Young-LIT project activities, to deal with them together. The second reason is that the outcome of the activities started and not fully concluded in WP2 was achieved in WP3 and activities were not always so clearly chronologically divided, but very often partners developed them in parallel.

So, from our point of view, it is better to describe them as one rather than two separate item.

#### Objectives

- definition of a common model for the editorial handbook (Style Handbook)

- setting up of literary workshops in schools or in libraries to supply the website with reviews and materials with the help of the editorial offices in each library

- active participation of students and teachers in the workshops activities through reading, writing reviews, articles, illustrations, etc.

- promotion of a mutual exchange and debate on books for young people and authors between 14-18 years old students

#### Activities

The final version of the common part of the editorial handbook (Style Handbook) was completed, translated in English and sent by e-mail to all partner. Each partner started to work on their own section.

During this phase each local co-ordinator, following the project guidelines, continued activities for the creation of the literary workshops in schools or libraries, working with schools or directly with the students involved.

Italy

The local co-ordination team in Bologna was organised as follow:

Local project co-ordinator: Fabrizia Poluzzi

Biblioteca Sala Borsa manager and project leader: Anna Maria Brandinelli

Library editing expert: Tiziana Nanni and Assunta Serenari

IT expert: Roberto Di Loreto

The message was sent in September to all the high schools located in Bologna. Schools replied slowly but positively, especially classes with pupils in the 14/15, 15/16, 16/17 17/18 age range. The response from classes in  the 18/19 age range were fewer, because in Italy the students of this age range have to sit for their final examination, and their teachers often do not want to promote any additional activities. In any case,one class with 18/19 year old students has been found to take part in the project. More classes than required were found, but they were asked to wait until the end of November before becoming involved. The idea was to give them an entire series to review: the local team thought of a series for young readers focused on social problems such as nutritional disorders, drug dependency, etc. This series is often criticised by young people, so it would bevery interesting to know what students thought  of it.

Eight high schools joined the project in Bologna (Liceo Fermi, Liceo Righi, Liceo Sabin, Liceo Laura Bassi, Istituto comprensivo di istruzione superiore Crescenzi-Pacinotti, Istituto Aldini Valeriani Sirani, Istituto Rubiani, Istituto d’arte di Bologna) participating in the activities concerning the reviews, articles and creative writing, with a total of 10 participating classes.

Also an experimental virtual workshop was tested with a high school in Rome, the Istituto Tecnico “N.Macchiavelli”.

The book list prepared by the director of the youth sector of the “Sala Borsa” library in Bologna, Tiziana Nanni, was sent to the other countries and subdivided into age groups, according to the indication provided by the publishers.

Having identified the five classes wanting to participate, one per each age group, the books were distributed for reading; an educational co-operation was established with the teacher and the deadlines were defined at first for the reading, then the writing, to be followed by the proof-reading.  Discussion meetings with the classes were scheduled according to the teacher's requests and availability.

The local Italian team initially met all the schools which had replied positively to explain to them the aim and the objectives of the Young-LIT project.

A second meeting was organised to deliver the books and the Style Handbook explaining its purpose.

There was a third meeting only for the schools which asked for it to be organised.

Ten books were delivered to each class. The choice was focused on recent well written novels with a hero and heroine and focused on subjects that are interesting for teenagers, such as finding out about yourself, relationships with the opposite sex, etc. Furthermore, two special series for young adults (FRONTIERE and I CORTI – published by E.ELLE) were reviewed by students.

In the Italian workshops students were not free to choose books from the list, but they were given a title asking them to read, exchange and discuss the books between them, and to take on the role of journalists or creative writers, they had to act as professionals.

It was not so easy to find books available in translation in the other four languages, even though it would have been very interesting to use the same texts for all in order to stimulate an on-line debate and the exchange of impressions and comments between students of different countries.

Some common books were found in the Italian and English list. One common author was found in Italy and Norway, Carlo Lucarelli, although he is known in Norway for his book “Almost blue” rather than for his books for young people, which were those included in the Italian list.

So, starting from these core books, other titles were added to the original list of books and were then distributed to the interested classes.

As for the articles written by students, six authors were chosen (Marcello Fois, Carlo Lucarelli, Gian Piero Rigosi, Nicoletta Vallorani, Barbara Garlaschelli, Massimo Carlotto), having first looked for information about them on the Internet, with the aim of making searches easier for students. At the same time publishers were asked to be available to be contacted by students, and some replied positively.

Between November and December the Style manual (common part and Italian section) was distributed to both teachers and students.

After the initial phase contacts between the editorial office and students were kept by e-mail or phone.

Several art colleges and schools from Bologna and Milan (Accademia di Belle Arti di Bologna, Istituto Rubiani, Istituto Superiore di Disegno Anatomico, Istituto d’Arte di Bologna, Istituto Europeo di Design di Milano,) joined the project to participate in the illustration sections.

Most of these schools of art had already been involved in the “Biglia di vetro” initiative.

The local project team met them initially to explain the Young-LIT project and to deliver books. Usually, as mentioned above, students were given only a copy of the back cover and the first pages of the book because they were not interested in reading the books, but only in drawing illustrations. However, a number of students asked to read the whole book.

Bergen (N)

The team in Bergen was organised as follows:

Local project co-ordinator: Karen Marie Loge, Trine Kolderup Flaten, Turid Hitlad

Library editing expert: Karen Marie Loge and Henrik Nielsen

Bergen Library director: Trine Kolderup Flaten,

IT expert: Gary Allen

In Bergen they decided to work directly with 17-19 year old students, rather than just through schools or teachers. In fact, the project-leader visited three local high schools and talked to all the second year and final year students.

Furthermore since mid September 2001 the library had participated in another literary project involving young people and so these students too were invited to join the Young-Lit project.

The library also contacted the Art Academy in Bergen and put up a notice and information about the project hoping that students from the Art Academy would want to illustrated the reviews. They were told to contact the project leader in the library and several art students showed up and wanted to know more about the Young-Lit project. The project-leader talked to the students, handed out the book-list and the style manual, and demonstrated Luvit and how to use it. Several students were interested and wanted to join the project.

The project-leader made a list of about 45 titles, fiction and poetry in English or Norwegian, books young people read, want to read or should read (from a librarian’s point of view) for the young students to review. The students were told they could either choose books from the list, or choose books they had read and enjoyed, or a book they wanted to read and review.

The local team organised workshops deciding together with the students that the students should bring the reviews to the library on floppy disc, e-mail or in hand written form after the Christmas vacation. In the meantime, the local project co-ordinator met the students in her office on request, and talked about the reviews and what was expected. She also explained to students about creative writing and short remarks, where they could write or publish their own writings and poetry. They also decided that the students could review favourite books not included in the list, as we thought the reviews could be more interesting and fascinating if they enjoyed the book.

As for the Style handbook, the local project co-ordinator in the first phase started to translate parts of it into Norwegian, but as in Bergen the local team has worked with young adults aged 17-19, they all spoke and read English quite fluently, and since they intended to work and publish in English, they found the English version sufficient. Copies of the English version of the common section were handed out to the students and together they  went through  the requirements for the reviews and the essential parts of the manual.

Milton Keynes (UK)

The team in Milton Keynes was organised as follows:

Local project co-ordinator: P. Scott Garret and Chris Murray

Library editing expert and IT expert :: Chris Murray

Two schools were selected to take part in the project, Denbigh and Lord Grey schools, both within the Milton Keynes Local Education Authority catchment area. However, the individual catchment areas for these schools are completely different. Lord Grey has a catchment that includes some of the most socially and economically disadvantaged areas in Milton Keynes, whilst Denbigh is the complete opposite, surrounded by a relatively wealthy and prosperous catchment area. Denbigh school has a higher level of achievement in local league tables than Lord Grey.

30 pupils from Denbigh and 50 pupils from Lord Grey took part in the project. The local project co-ordinator, the librarian Paul Dorney, worked directly with the schools, pupils and teachers.

From Lord Grey, the contact for the project at the school was Isabella Coles, the school librarian, who was very keen to be involved and who would co-ordinate the English department’s involvement. It was decided that they would initially involve 2 classes of year 8 students and make it part of their English curriculum lessons.  Interestingly, those students who were very keen formed a reading group that would meet every Wednesday during the school lunch hour, in the library.

From Denbigh, the contact for the project at Denbigh was Janet Stone, the Head of English and the teacher with responsibility for the library.  Here it was decided that they would conduct the project on a purely voluntary basis.  They advertised within the school and the Young-LIT local co-ordinator was invited to introduce the project to those volunteers. This method of working produced a small group of keen readers of all ages who would be producing the reviews.

The first task was to prepare a recommended list of 50 titles with thematic guiding and age suggestions.  It was hoped that this was a well-balanced list that encompassed material suitable for the age range of the project, different reading levels, both sexes, and that covered a wide range of themes. The list was drawn up from reading lists produced from various sources including the Internet and the Library Association in consultation with teachers and colleagues.  It included fiction both contemporary and classic in order to gather the true opinions of the young people involved in the reviewing.

The pupils from both schools would also had the opportunity to work with local independent journalist Lee Scrivens as a follow up to the Young-LIT project experience, as an attempt to provide a different kind of experience, from the journalist’s perspective. It was also an attempt to sustain the project locally, beyond its current life span, ensuring that pupils remained interested and engaged in this important activity.

A set of books from the recommended reading list was purchased for each school.  These were distributed to the schools with an emphasis on freedom of choice from the list.  It was also explained to the schools that if the young people wished to read and review other material, for example the next book in a specific series, then this should be encouraged so as to maximise review output.  Special stickers were produced for the project so that the collections could be identified within the schools.

As a Librarian, Paul Dorney, the UK Library expert, tried to steer away from any possible censorship with regards to the reading material.  However, as the age range of the project was quite wide there was a significant difference in the reading levels.  It was felt, after consultations with the teachers involved that some of the material that was suitable for 17-18s would not be suitable for 12-13s.  This material was removed from the collections at the discretion of the teachers.  It was understood that although young people should have freedom of choice, any material that was deemed unsuitable could not be recommended to them by an educational institute as this could have repercussions from parents.

It was decided that in order to encourage involvement in the project, the Style Manual for the UK should be as simple and as fun as possible.  With this in mind the partners were contacted to examine their manuals and adapt these for the UK.  Although still containing the information needed about the project, the emphasis here was on encouragement and guiding.

Ronneby

The team in Ronneby was as follows:

Local project co-ordinator and Library editing expert: Lena Mattisson

IT personnel: Peter Blaschke

A recommended reading list was prepared for the kick-off meeting in Bologna in October. It was somewhat revised subsequently, in order to find as many common books for the four countries as possible. This list was not distributed to the schools and teachers but was used more as a tool for work in Ronneby. Many of the pupils had their own propositions which were also suitable for the project and so they were told to chose freely.

In Ronneby four schools were found in with pupils in the appropriate ages for the project.

The first school is Bräkne Hoby skola, a school in a village 15 kilometres from Ronneby. It has 462 pupils in the 6 –16 age range. Together with the teachers we decided that it would be best to form a group of interested pupils. The group consisted of 19 pupils aged 14-16.

The second school is Kallingeskolan. It has 370 pupils in the 13 to 16 age group and is situated in a suburb of Ronneby. Also the local co-ordinator started to work with a group consisting of 29 interested pupils. Some of them left the group during the project and some new students joined in.

The third school is Snäckebacksskolan in the centre of Ronneby, with 500 pupils in the appropriate age groups.

Here one of the teachers wanted a whole class to participate with all students aged fifteen. The good thing about working with a whole class was that you get all kinds of pupils to take part in the project, even those who normally do not read.

The last school is Knut Hahnskolan, the only secondary school in the municipality of Ronneby. Here too the work was carried out with a group of interested pupils, although it was very difficult to find students that wanted to participate, so that the group was rather small.

In the secondary school  Knut Hahnskolan a whole class of art students was involved in the image part of the project. They were second year students, and the teacher made it a part of their programme to illustrate a given book. The results differ very much, according to ability and talent.

The workshops were held mainly in the schools, together with the teachers. The reasons for that are the distances, as many pupils live far away from Ronneby and would not have been able to take part if the workshops had been held in the evenings.

The local team visited all the schools at least twice. they visited Kallingeskolan  more often since the teachers there were very interested and organised discussions around literature in that group.

LUVIT was introduced and used as a  working tool, for all groups. This was been very helpful, since many of the pupils had computers at home and could work from there. Much of the communication between the editorial group and the pupils was via LUVIT. Every group had their own login and students could read one another’s work, it was also a good tool for direct communication in LUVIT, in fact it is possible to see who is on-line and to communicate directly.

The editorial group consisted of one local journalist, Jan Hinderson, and Lena Mattisson, the local project co-ordinator. At the beginning of the project they had a meeting to discuss how to carry out the work. Afterward most of their contacts were kept via e-mail and Luvit. The pupils send their material to Luvit and they read and commented upon it and sent it back to the pupils to modify.

The Swedish Style Manual ”Skrivarhandboken” was written, printed and distributed to the participating schools during November and December.

The Style Manual is in parts a translation of the shared English version, but adapted for Swedish pupils and the way language is used. The formal instructions on how to write are not published in the manual, but there are two recommended addresses on the Internet, one from the press and one from the official Sweden. The pupils was also told to use the spelling and the word count function in MS Word.

#### Main results

- Final version of the Common Style handbook and national parts (see ANNEX III - Style handbook : Common part, Italian Style handbook, Swedish Style handbook, United Kingdom Style handbook)

- Workshops and editorial office start up and books distributions in schools and libraries (see ANNEX IV - Booklists Italy/Norway/Sweden/United Kingdom)

#### Comparison of work done against plan

Some slight deviation from the original plan were encountered :

- in Italy the number of workshops was increased from five to ten, due to the high number of positive replies from schools and to the number of titles distributed.

- in Norway the local team decided to work directly with students meeting them in the library, without involving their school teachers.

- The schools involved in the UK were not specialist arts colleges. The local co-ordination team therefore decided to focus on the written text as the most important element of the local project, rather than to dilute people’s efforts by asking them to contribute graphic material as well. This further dimension to the project might be considered for future follow-up.

### 4.2.4 WP04Materials collection and website design

Starting date: January 2002 Ending date: February 2002

#### Objectives

- Collection of materials produced in each workshops

- Work of the editorials office on materials collected

- Overall design of the Young-LIT website (WP04 was aimed at providing a clear understanding of the structure and the contents of Young-LIT)

#### Activities

First of all an evaluation of activities implemented in the last two workpackages was done by all the partners through e-mail contacts, in order to decide how to proceed.

Activities developed in WP 02 and 03 were: book choice, identifying common books, distribution, contacts with schools, work on the materials, preparation of the style manual, correction and transmission of texts also translated into English.

The situation did not seem homogenous in the four countries, partners had to face different problems related to their own school system.

At Milton Keynes there were initial difficulties in finding classes due to January testing, although they eventually succeeded in finding them.

As the partners of the project had agreed to use LUVIT as a notice board for Young-LIT, the local co-ordinator went into the schools to explain how this worked. Where this worked very well for the dissemination of information between partners, both schools involved felt that the young people should be able to e-mail their reviews directly to the local co-ordinator as editor. Those young people who had access to a PC at home expressed the need to be able to contact the editorial office through e-mail so that material could be sent back and forth whenever needed. This was a useful thing for both parties and helped to speed up the flow of information.

As the reviews were being e-mailed to the editorial office, it meant that it could edit what needed to be done and then post the reviews on LUVIT. Initially work was placed on the LUVIT site, and later moved permanently to the Young-Lit website.

At Ronneby the students worked a lot and the organisation of workshops was greatly helped by LUVIT as well as by the co-operation of an author (Per Nilsson) and a journalist (Jan Hinderson).

In the course of the project, one of the authors, Per Nilsson, who had been much read during the project, visited the groups and met his readers. He writes about the difficult things in life, and has received several awards. So the students worked to prepare themselves for his visit and they asked him a lot of questions.

Another aspect of the Swedish workshops should be reported, i.e. the working language. Since the beginning of the project some of the participating students wrote their reviews both in Swedish and in English, which was a secondary benefit of the project. But as the project proceeded the local co-ordinator realised that the knowledge of English was not as widespread in Europe as she had thought. Therefore she no longer forced her students to write in English as well as in Swedish and a translator began working with the Swedish texts.

At Bergen the local project co-ordinator had another meeting with the students in January. In the Norwegian workshops they worked with LUVIT too, using it as a tool for submitting the reviews, chatting or discussing with other students on the programme. After the winter vacation they had another meeting with the students where author’s profiles were also discussed and a selection was made of the authors they wanted to interview. The short list was narrowed to three authors (Pedro Carmona-Alvarez, Gunnhild Øyehaug and Ingri Egeberg) and the students found the interview and the talk with the authors very inspiring and fascinating, and maybe the most exciting part of the project.

At Bologna, the working groups were different from the start, first of all because there were two types of high schools involved: two "licei scientifici", all equipped with a computer classroom, with attentive and interested students; two technical institutes, fully equipped with computer classroom, whose students were not very interested in reading books or writing, and with an Arts school, where IT provisions were not adequate, with very lively and vociferous students.

In Italy, however, the situation was peculiar especially in the month of January, as protests were raging in high schools, with closures and occupations of school premises which caused the work to slow down as well as end of term tests and evaluations. Also the opening of “Sala Borsa”, its success which far exceeded expectations, and some in-house office shifting turned into hurdles for the setting up of the editorial office which was established with great effort, working mainly by e-mail to keep contact between workshops, editor, translator, and technician for data input.

Apart from that, the first part of the work proceeded smoothly; with difficulties emerging with the text proof-reading.

Teachers stated their interest in the style manual, but they left students to manage it on their own, without any control on their part, and often delegated the sending of material. The result was that not all materials had been received after the Christmas vacation, they were sent irregularly, sometime more than once and by individual initiative.

The problem in Italy was that literature teachers usually do not use the computer which is located in a specific classroom, which students may access according to a very strict agenda which is set once and for all at the start of the school year. This was not a problem in the partner countries where things work in another way and, in some cases,  every classroom is equipped with one or more workstations, which teacher use directly as a teaching tool.

Considering the situation of Italian schools, it is easy to understand why LUVIT was used less in Italy than in the other partner countries, even though its use was possible and would have speeded up the information flow. Nevertheless a lot of materials were posted on LUVIT for a preview and to be able to compare them with partners’ materials.

As regards the articles, in Bologna the workshops were held for the last two classes of the high-school cycle, 17- and 18-years-old students.  Of each author students read  the books for children, young people and adults;  did some research on the Internet, and contacted authors with the help of publishers. The authors chosen were: Carlo Lucarelli, Nicoletta Vallorani, Marcello Fois, Barbara Garlaschelli, Massimo Carlotto, Gian Piero Rigosi.

Students did two interviews on line with two Italian authors: Nicoletta Vallorani e Barbara Garlascherli.

Their publishing house (ELLE) gave them the authors’ e-mail addresses, so classes prepared n outline of the interview explaining to the authors the aim of the Young-LIT project and its programme.

As for illustrations, given the project duration, both the Academy and the Institute for Anatomical Drawing were involved very late, so they participated in the on-line magazine only at a later stage. Also the Arts Institute had some problems in sending materials and teachers were asked to make a selection of the materials received; the editorial office’s proposal was to include only relevant illustrations, rather than those with artistic purposes only, or which were not clearly displayed on the web site.

Materials collection

In Bologna it was evident that, even in high schools, students were quite familiar with reviews.In the arts school one girl remarked that our initiative would help students who, forced by their teacher to read and review one book a month, would find their tasks already done, as they could just download it from the Internet.

The work produced by workshops in all countries was of the highest quality. This surprised the national project teams, not because they did not believe the participants would eventually be capable of this, but because it seemed to have been produced with relative ease, which is a sure sign of enthusiasm for both the subject and the project.

In a sense, the project has been an important trigger in motivating the participants. They realised that there was a real, international audience for their work, that other people outside the school really would read it with interest and therefore made the greatest effort to produce works of quality, with extremely interesting results.

In general the material was interesting, but too school-like; the students tried to express their opinion in an objective way, as requested, but they did not dare make any slating remark, which they tend to do informally with no problem.

The same problem was found for the articles, which were good, well written and with a good layout, but essentially flat, without a definite critical stance, while, when the local co-ordinators went to the meetings with students, they showed quite plainly their lack of interest. The remarks expected were in fact voiced but only verbally, and for some classes with a very heated discussion and much participation.

For this reason, partners agreed to add a “short remark” to the reviews in order to make students take an explicit stand. The range of terms chosen was the following:

ABSORBING

INTERESTING

AMUSING

DISAPPOINTING

SOPORIFIC

Another important point emerged from the materials collected.  In Italy, the list of reviewed books referred only to narrative for young adults as the goal of the European project was to explore this type of narrative, listen to the opinion of young people and establish contacts with authors, publishers, and readers, while in other countries  books for adult readers were included in the lists, as partners agreed on the possible presence of classics. The reviews submitted proved that young people are not very keen on reading book series dedicated specifically to their age groups, and this fact, although it did not emerge clearly, found confirmation here.

So, in order to highlight these findings all the local teams collected students individual voices and decided to enclose some flash items at the closing of the articles, to allow them to express their real opinion.

However, in brief the students say that narrative specially written for young people is superficial, packaged around contents supposedly suitable for them, which do not stimulate them; some believe that the age recommendations should have indicated younger readers, at the most, lower high school students. Some think that they should be recommended to young people who do not like to read, because they are short, easy to read and you get rapidly to the end; other again think that they may be introduced in schools, but only for specific issues, with regard to emerging problems and issues. For example, if a student suffers from an eating disorder, he/she may be advised to read the book dealing with that issue, but nothing more than that.

Plan of the website graphic structure

In this phase website technical aspects were discussed by e-mail between the partners. A proposal for the website graphic structure (see ANNEX V – Draft of website structure) was prepared by the IT experts of the Municipality of Bologna and a demo was put on Internet so that it could be seen by all the partners before the meeting in Bergen.

The idea initially proposed by the Municipality of Bologna, to have a home page for every country and one common international home page, with a replica of the same main web structure for every country site was definitively abandoned. So IT experts worked on the structure of a common European site in English and one common database.

In the first meeting the different sections of the on-line magazine had already been discussed, but they were slightly changed. The website sections proposed were as follows:

What is it?: a description of the Young-LIT European project, its aim, its objectives, the partners, etc.

How to do it?: How schools or individual students can take part in the editing process, how to participate in the Young-LIT on-line magazine, writing reviews or articles, drawing illustrations, how to send e-mails with txt or jpg attachments, etc.

Style Guide: The three Style handbooks (Italian, English and Sweden), with the specific languages rules.

Italy/ Norway/ Sweden/United Kingdom homepage: All the contact details of the four editorial offices in the four European libraries

Bookcase: list of books proposed with reviews and illustrations made by students, when available.

Reviews: Collection of reviews.

Pictures: Collection of illustrations for some of the books reviewed.

Articles: Articles written by students on local authors, work of fiction that particularly stimulated the young readers’ imagination, articles on European literature for young people, curiosities, studies on a publisher’s series or interdisciplinary projects with the English teacher in collaboration with other student partners, articles and interviews with authors

Creative writing: this section is dedicated to those students who write poetry or stories and who see themselves a bit as writers.

Flash: free student’s opinions and remarks

Each sections was included both in the “back end” area open only to the four editorial offices and in the “front end” area open to all website visitors.

BERGEN meeting

At the and of this project phase, partners met again for the Second Steering Committee meeting held in Bergen on 25th and 26th February 2002. This was an occasion to debate and discuss the problems and difficulties encountered during the project’s starting phases.

Subjects mainly discussed were:

- ITC problems and equipment available in schools

The situation is different in the four countries but, as mentioned above, the worse situation seemed to be in Italy, where teachers of literature have problems in accessing IT equipment, unlike teachers in Ronneby where they have a PC and an Internet connection in each class and in the library too.

- Forum

Partners discussed the advantages of having a forum on the project web site. They agreed that it would be an important tool to stimulate students to talk about books, saying what they really think like in a chat. Publishers could be interested in promoting this type of initiative, as it could be very useful for them.

Since there were some management problems that would not be easily overcome in a short time, they found a temporary solution: to exchange the “quiz and game” part with a section called “flash” where students’ short remarks on books, authors, publishers, series, etc would be posted. The possibility of a forum should be considered as a future development of the Young –LIT website.

- Illustrations

As described above not all partners were able to contact art schools for illustrations as the Italian workshop had done. In Milton Keynes and Ronneby there are no professional art schools, so they asked their students to write reviews or to draw illustrations. All partners agreed to leave both the possibilities open, professional and non-professional illustrations.

- Plan of the website graphic structure

The website technical aspects were discussed and the web site graphic structure described above was presented by the IT experts of the Municipality of Bologna.

Some of the changes proposed and subsequently inserted in the website were:

Bookcase Section

BOOK LIST

- Possibility of insert the book cover beside each title

- View of the last eight titles on each page, with the others available through buttons to return to the previous page or move to the next. The same solution would also be used in the other website sections (reviews, articles, etc.)

Section Reviews

SEND

- the fields “review title”, “class” and “teacher” should remain optional

- “book title”: to avoid mistakes in the data input it would be better to have a scroll bar or a compulsory path to follow, leaving students the option to input a new title not yet inserted in the bookcase.

Section Flash

- Replace the“quiz and game” section with this one.

This change was proposed because, at least in the early stages, the work of the editorial team would have been hectic, so some doubts had emerged concerning the last section, which at the start had been called Quiz and Games. It had been proposed because it might have been attractive for students, helping the magazine to shed its rigid school-like outlook. However problems had been raised concerning the difficulty in managing this section which needed to be updated weekly, publishing the right answers and the names of the winners, and sending out any prizes to the winners.

- Main points agreed in the Bergen meeting

- Extension

It was agreed to ask the European Commission to extend for one month the eligibility period to have time for testing the website structure and to evaluate the dissemination of the project and students’ involvement after its opening phase.

- Site

- -To have one common European site in English (with the option of inserting materials in all languages) and a common database

- The web structure should be the one illustrated and discussed during the meeting, with the changes proposed

- Children book fair

The Municipality of Bologna should take part in the fair with an installation in the Librarians’ Association stand to disseminate the Young-LIT project and to distribute materials and information brochures on the project.

- Video conference

A virtual meeting would be organised in April after the Children's Book Fair, if partners and co-ordinator felt it necessary.

- Final meeting

- Was decided to hold the final meeting and the final event in Bologna, on May 27th and 28th 2002

- Partners agreed to consider the possibility of taking alongsome of the students involved in the project to the final event in Bologna.

#### Main results

- General agreement on the plan of the website structure (see ANNEX V – Draft of the website structure)

#### Comparison of work done against plan

No Deviations from the work plan were made

### 4.2.5 WP05Website implemented and project dissemination

Starting date: February 2002; Ending date: June 2002

#### Objectives

- creation of an on-line network for schools and libraries which provide materials for the website

- implementation of local editorial teams’ activities through proof –reading , input and updating of the materials collected

- website start up

- project dissemination activities

#### Activities

Further collection of materials, difficulties and feedback

During this project phase the editorial offices’ activities continued collecting and revising materials from schools and students.

The last months of work were really hectic, and were spent trying to contact the late-comers; almost all the material was assembled, but not all of it, and for this reason there were some reviews without illustrations and vice versa. The situation per se was not considered a reason for concern; it could even spur students, once the school term was over, to complete the magazine. Planned interviews or unfinished articles were completed and enclosed later.

The main reason for the missing pieces and mishaps in the last part of the project was certainly due to the imminent end of the school term; the student were busy preparing for tests and examinations, teachers with evaluations and administrative work, so that even simple communication slowed down.

However the deeper reason for the difficulties encountered was due to two factors which have already been partially mentioned, which seemed to characterised especially the Italian workshops.

The first was the type of reading material proposed, books for young people which were not appreciated by young people who, in the age group considered by the project, read extremely different things, unspecific ones and certainly adults' books. This criticism has to be addressed to publishing houses applying an outdated model no longer followed by other European countries. Students of vocational technical schools seem to  like this type of books the least; while students of the "licei" participated in textual analysis and literary critique, although slating the majority of the books they read, others started reading but soon got bored. In the project the analysis of young adults' books was enclosed on purpose, as it was considered that a European comparison with young readers would have been very interesting; giving fruitful results.

The second factor was related to the IT network of Italian schools. There are no workstations in the classrooms and students can use computers only by booking the IT classroom and using it when it is not used by teachers for their lessons. Therefore, all input to the "virtual" editorial room was made by some students from their PC, and this often created some mishaps.

The picture of the workshops in the four European countries was not exactly the same, and this was due to several factors that from the beginning of the project made the research even more significant, rather than undermining it.

First of all, in the other partner countries much less material was collected than in Italy, but this was only due to the fact that work in the project leader country was started even before the approval of the project, precisely in order to tune up and test the working hypothesis and lay the foundation for the co-ordination work.

The second relevant difference was due to the material itself on which the work was based. Young adults' books, the focus of the research, in Italy are part of specific series, while this is less so in the other countries. As a result, the books being proposed were generally accepted positively in partner countries, while in Italy they were disputed attesting the fact that Italian publishing offer lags behind vis-à-vis the rest of Europe. So books proposed for the UK, for example, with many classic titles classics would have been much more appreciated by Italian students too, and this emerged clearly when these books were distributed after the second meeting.

This can be considered the most relevant result of the project research, stressing how the opinion of Italian teenagers essentially corresponds to their Norwegian, Swedish, British peers'. Therefore, after this pilot experience, the partners’ intention is not to keep the current book list in the website; it should be updated immediately or replaced by free choice in order to stimulate future participation by young readers.

As regards specific difficulties at the end of the workshops, which coincided with the final school tests, exam preparation and the arrival of spring all  partners were in the same situation.

However in general the work was a big success. The quality of review work was on average good.

All teachers appreciated the initiative which strongly fostered book reading for young people, also as an additional element for their curricula. Many schools have stated their intention to repeat the experience next year with an increased number of classes.

Some additional review conclusions emerged also from the material collected in the Milton Keynes workshops that are common to other countries’ experience.

The first striking thing about the project was that those who provided reviews for the website were predominantly females, which confirms current trends, with girls reading more than boys.  There was, however, no significant difference in the level of the reviews between the two sexes.

When left with a free choice from the list, it was interesting to see that multiple reviews for particular titles were submitted. Perhaps this was due to word of mouth recommendations between the participants in the project. It was also interesting to note that many of the reviews were submitted stating that the reviewer chose to read a particular title because of its appealing cover. This may not be the way in which books should be selected, but it does provide interesting information for publishers about what appeals to young people and how they should look at marketing titles aimed at the age group.

The overall feeling from talking to the groups is that between the age of 14-18, young people find alternate means of entertainment, television, computer games, socializing etc.

Reading does not necessarily stop but transfers to newspapers and magazines as a preference. Those young people who enjoy reading and are keen readers use this time to experiment more with adult fiction, as it is perceived to have more credibility than the fiction written specifically for them. This mindset comes from a lack of encouragement and guidance in their selection of fiction.  Hopefully this project gave them a motivation to read more of this material before moving on to adult fiction.

Even if they are not inclined to read, young people 14-18 begin to form opinions and like those opinions to be heard.  The Young-LIT website provides a forum for these opinions and at the same time uses this enthusiasm for criticism to steer them into reading more of the fiction written specifically for them.

Materials selection

Having collected all the materials, the technician in every editorial offices worked on data input after the correction and proof-reading by the language expert and editor, with the proper layout of articles, adding the missing data.

When the Style Handbook was created partners thought that it would lighten the burden of the editorial team; unfortunately, after the materials were collected, local offices realised that they needed to be thoroughly "cleaned-up", as often the students forgot to indicate their names or the name of the school, indicated the wrong publisher, did not mention the series nor the year of publication: therefore the initial activity was very hard for the editorial staff, with several key figures having to sit around the table, including a technical expert, a language expert.

As for the quality of collected materials, of course the problem was faced by each editorial offices. Although the quality of work sent in by students was very satisfying in all the four countries, sometimes editorial offices had to send back some essay as insufficient.

But is important to differentiate, as regards the workshops held in schools, between the guided and free essays. Some classes worked with their teachers and the text were really the result of discussion and research, while others were written individually without any guidance. As for creative writing, almost all the texts were sent back to the students with some remarks, and they were partly amended. Others still were sent back because too long.

The problem of selection had also to be faced after the website start up, when students would enclosed their essays autonomously. Partners agreed that some form of censorship might need to be applied only on provocative materials, with taboo words, or unsuitable polemic. As for quality, it would be useful to create a correspondence between young people and editorial offices and for this reason they should be required to enclose their e-mail address or a telephone contact number when they input new materials (reviews, illustrations, etc.).

For illustrations a selection was likewise necessary, which should be much stricter when students could no longer count on the school as a filter, or buffer, in compliance with the layout of the initial project. As for the Italian workshops, about thirty illustrations were eliminated as the teachers of one school (Art Institute) asked the workshop team to participate in the choice of illustrations for the website.

Dissemination activity: Children’s Book Fair

As envisaged in the project work plan, with the public lunch of the Young-LIT website, the project shifted from local to national for each editorial team, and became transnational for the four editorial teams together. Therefore all the workshops activity, as it was carried out previously, had to be concluded, and a new virtual one started. From this time onward, the editorial team no longer needed to look for the schools intending to participate, but the schools themselves would contact the team, having seen the magazine. Therefore it was very important that all high schools, libraries, publishing houses, authors, and facilities catering to students of the age groups indicated, should be informed of the Young-LIT site and know its address in order to browse and “leaf through” it.

Each central library had to develop a canvassing activity of dissemination, contacting all the major national libraries in order to illustrate the project and ask them to send information to schools.

So an important task to be developed in this project phase was to establish a chain of information in order to reach as many people as possible and to spread information about the Young-LIT website.

The most important event for the Young-LIT promotion of the on-line magazine and website was the children's book fair, which is held every year in Bologna and in 2002 was scheduled on April 10th,11th,12th. For this very important occasion the project co-ordination team in Italy organised not only a presentation of the project but also an installation. The fair is attended by a lot of people active in the field of youth literature, the same target the Young-LIT project addresses, such as authors, illustrators, librarians, publishers, teachers, etc.

For this event an information brochure on the Young-LIT project was prepared and printed in many copies, to be distributed during the fair (see ANNEX VI – Young-LIT information brochure).

The Librarians' Association was present with a stand which is always a point of attraction for libraries and schools, and so copies of the project brochure were left there.

Furthermore, representatives of the Italian co-ordination team attended the fair, which was an occasion to meet and talk about the project and its progress and to participate in the Illustrators' Cafe. This was a point were some innovative projects in the field of literature for young people could be illustrated and presented to people attending the event.

The Young-LIT project objectives and aim were illustrated, a demo of the project website was presented and some of the materials collected (reviews, illustrations, etc. see ANNEX VIII – Collection of illustrations made by the Young-LIT artists) were showed to the public by the project co-ordinator, Mrs. Anna Maria Brandinelli, manager of the Sala Borsa Library. Also a publisher was invited to talk about how publishing houses select literature for young people. Also some of the students involved in the Italian workshops (literature and illustrations) took part in the discussion on the reasons why young people do not like what is written for them, and the most important result of the project research turned out to be quite interesting.

The website

If the collection of material was quite difficult, especially in the last part of the school year for the reasons described above, the same applied the work for the designing of the web site, which was ready later than originally planned. The website structure and design was as agreed by all the partners during the meeting in Bergen on February 2002 and described above (see ANNEX IX – Young-LIT website demoo) and as for the graphic design it was enriched by illustration made by Young-LIT artists. As soon as it was ready and available in a sort of Intranet open only to the four local teams, each editorial offices started to input all the materials collected from its workshops. So a first phase of testing and trials started to check website functionality and obtain an initial feedback from users. The site had to be adjusted, as some things did not work well; so all the negative comments were collected by the partners in order to make the necessary adjustments and to have a fully working site for the final event in May.

Final Steering Committee meeting

At the end of this project phase the final partners meeting was held simultaneously with the final event.

It was organised in Bologna, on May 27th and 28th

Partners had the chance to report on activities developed in this phase, to discuss the difficulties faced and the results achieved.

During this debate issues mainly discussed were:

- List of books

Partners agreed that for the future prosecution of the project, students should be free to choose books and to propose new books not included in the list yet.

-	 Website

Partners voiced their comments on the website proposing some changes and improvements on the bases of their experience in the input activities done to test and input contents and materials collected from their local workshops.

- Editorial control and authors’ contact details

Partners wondered what would happen if the editorial office receive a text not in his own language or that needed to be partly amended because too long or not sufficiently detailed, as had  already happened. How could the editorial office check the content in this case? It might be possible to send it back to the author to have an English version or to request adjustments.

In the current website’s structure young people were not requested to give their details when they sent reviews, illustrations or other materials. For the reasons mentioned above partners decided that for the future authors should be required to enclose their e-mail address or a telephone contact number to be used only if necessary.

So partners agreed to keep author’s e-mail address and/or telephone number only in the “back end” area, the manager side and only until the reviews (or creative writing) or illustrations were published on the site. After this operation every contributor’s contact details would be cancelled from the common database and an auto-reply message would be sent back to the author saying “your work is been published and your contact details have been cancelled”.

- Section Bookcase

- In the “bookcase” FIND in the users’ part, there should be a scroll bar only with the publisher countries for the books already on the site. For the PROPOSE section in the scroll bar there are all the possible publisher countries.

- In the “bookcase” FIND in the ”front end" area, add a function “sorted by country”.

- In the “bookcase” section, add a small image of the book’s cover (in the user-site only) when available

- Add "sort by isbn" in the bookcase page

- In the "manager-part/books" page insert the buttons" add a picture" and "add a review"

- Genre

The genres list had to be changed and shortened to be used by all countries, since it created some misunderstandings between the four editorial offices:

- Illustrations

There was a problem with the size of illustrations, some of them were not entirely visible on the screen, and visitors had to scroll them. It was better to have a full screen view of illustrations.

- Final Report and Final Financial account

A timetable for the submission of the FFAR and the FR was agreed by the partners.

- Advertising and dissemination

It was agreed to go on with advertising and dissemination activities in each country until the end of June  and again in September after the Summer holiday.

- Project prosecution

It was decided to have a first updating exchange of e-mails by the first week of July and a second one by the middle of September, for an update on local editorial offices’ activities, website success and future prosecution.

Dissemination activities: the Final Event

As the project ended in May, following the original project plan, and schools were drawing near the end of the school year, partners in the Bergen meeting agreed to hold the final Steering Committee meeting and the Final Event in Bologna at the end of May so that students could attend it before breaking for the summer holiday although if they were quite busy with final tests. With the website public launch, a new phase started to test if the magazine had found a readership, despite the imminent end of the school year, knowing it would certainly be very difficult to find students interested until the middle of September. In any case, at that point the Young-LIT research had ended and had provided the input materials to readers, publishers and students. The outcome of the project, although covering a small sample, was already detectable and confirmed partners’ expectations.

In fact, the focus of the project was fostering the dissemination of literature for young people, listening to  young people's opinion about it, and understanding why, especially in Italy, this age group seem not to read enough, comparing the situation with three other European countries, gauging where young people's interests lay, comparing young people's remarks and views with publishers' and authors' in the four participating countries, seeing market differences and providing food for thought and analysis. Young people are not satisfied with pre-packaged literature, and it seems that, while in Italy it is still booming, in the other countries the phenomenon is already on the wane, and publications of this kind are less in number.

Therefore the final meeting, specifically in its public outlook, was a very important moment to foster public debate and discussion on these issues and another crucial way to disseminate the project contents and results and to publicise the new website.

For this purpose the event was organised in order to have students possibly representing the four countries or at least part of them, because it was  important to have them speak in public about their view and their experience in the Young-LIT project, together with teachers, publishers and authors.

So all the Italians students and teachers involved in the project activities were asked to attend. Considering that it was a very busy time at school for the final exams, it was decided to hold the meeting in the afternoon to allow as many people as possible to attend.

From Bergen two seventeen years old students, Erika Bunting and Anette O. Jakobsen, who had been involved in the project, came to Italy for the final event

From Ronneby two fifteen year old students, Jennie Andersson and Ellinor Ihlström, accompanied the local co-ordinator.

No students from the United Kingdom were able to attend the event: while some countries have a flexible attitude to travelling with young people on project trips; in the UK the legislation for local authorities makes this extremely difficult.

A publishing expert was invited to join the event, to speak about the birth and development of narrative for young adults, today's situation and future prospects; how the market is moving; together with an Italian author (Marcello Fois), included in the list of the six authors chosen by students to write articles on, and a journalist who is an expert on Internet and young people, who is also a teacher at the University of Bologna.

The event was organised in the Sala Borsa Library, on May 27th afternoon, in the so- called “Piazza” which is located in the centre of the library and is a focal point, as all visitors to the library have to pass through it.

A programme of the event was prepared in the same graphic style of the project brochure (see ANNEX VI – Final Event programme) in order to guarantee the widest advertising of the event, the website and the Young-LIT project.

It was distributed together with the project brochure in all the city’s libraries, in the main bookshops and also in the University. It was also sent by e-mail to a mailing list including Italian publishers, the city’s schools and local, regional and national libraries.

The news of the event and its programme was also published on the sites of the Bologna city network, such as “Flash giovani”, a portal dedicated to young people, “Bologna Turismo”, the city’s tourist board site, etc

A press release on the event was launched some days before.

Articles were published before and after the final event in local newspaper and on the Internet, as well as in some regional and national websites dealing with schools and education (see ANNEX VII – Newspaper and Internet articles on the Young-LIT project)

The event started with the presentation of the Young-LIT project’s aim and objectives and the description of the experience of the actors involved.

Each partner was given time to describe their experience in the Young-LIT project. Chris Murray decided to speak himself providing information on the town and on the Milton Keynes Council and explaining their main activities, the role with regard to youth policy, their interest in becoming involved in the Young-LIT project and the results achieved .

For Bergen, Trine Kolderup Flauten and Karen Marie Loge decided to give some general information about the Bergen Public Library and then let the two students who had worked in the Young-LIT project speak about their experience in the workshop. Also, for Ronneby the two Swedish girls talked about their experience in one of the project workshops.

After a presentation and a description of the Young-LIT website contents and aim (www.young-LIT.net) - which had just opened to the public a few days previously - there was a round table discussion aimed at exchanging points of views and expectations between the actors and participants in the project, focussing on one of the main findings of the project, i.e. understanding why young people don’t like what is written for them. All the actors (students, local project co.ordinator, authors, publishers, etc.) involved in different way in the project took part in the discussion which turned out to be very interesting.

A lot of people attended the event, not only students already involved in the project and their schoolmates who had not yet been involved, but also library users who were curious about what was happening in the “piazza” and stopped to listen.

Other dissemination and advertising activities

Apart from the Children’s book Fair and the Final Event, which represented the wide dissemination activities envisaged in the project work plan, continuos project dissemination activities were developed autonomously in each partner country with different means, in order to ensure an increasing number of website visitors and consequently the prosecution of the project in the future .

In March a leaflet in Italian and English illustrating the project was prepared for the Young-LIT presentation in the Children’s Book Fair. Later it was also distributed in schools involved in the Young-LIT project and libraries, distributed with the programme of the final public event. The information brochure, together with the mailing list used for the final event, will be used massively in the future for an information campaign about the site envisaged for next September after the start of the school year, this time not only for schools in Bologna, but throughout Italy. For this purpose, further copies of the project brochure were ordered at the end of the project.

As for specific activities in the partners countries:

In Ronneby the project dissemination started as soon as the web magazine was ready. Since then it has won an award as a good page for young people from Barnboken.nu, a Swedish webpage about children’s literature. http://www.barnboken.nu.

Two newspapers have published articles about the project (see ANNEX VII – Newspaper and Internet articles on the Young-LIT project).

The webpage of the Municipality of Ronneby http://www.ronneby.se/pressmeddelanden/20020515.htm has information about the Young-Lit project.

The address of the Young-Lit Magazine was sent to the mailing-list skolbib. which almost all Swedish school librarians read.

Furthermore schools were contacted and hopefully students will start reading and writing when schools start again in august. Contacts have been established with national libraries, by sending a press release to their mailing list and a new delivery is planned in August.

Planned activities are to send information about the magazine and project to Skolverket, the Swedish central government authority for schools and to Länkskafferiet, a collection of quality links for pupils and teachers approved by Skolverket.

In Milton Keynes, to let people know that the website exists and what it is for, the local co-ordination staff worked with local journalist Lee Scrivens, who produces an independent magazine for young people called ‘DoWhat’, so the project and some young people’s reviews were published in this magazine when the schools in the UK return from their Summer Holidays In September information on the project will be circulated to every school in Milton Keynes and to every Local Education Authority in the country, as this is the only way of generating a lot of increased interest in the project, both locally and nationally.

Also in Bergen dissemination activities after school summer holiday have been planned. In September information on the Young-LIT project will be circulated to every school in Bergen and to every Local Education Authority and Library in the country, through national networks.

#### Main results

- Website implemented (see ANNEX IX – Young-LIT Website demo)

- Final event and website public launch

#### Comparison of progress against plan

In relation to the criteria and timetable agreed by the Consortium and reported in the project workplan, some changes occurred. In particular, some additional time was required to carry out the final implementation of the website, due to technical problems with the website creation that required extra work. So the launch of the website was postponed and the first issue of the on-line magazine was delayed from the end of March to May 2002.

It was decided that a videoconference, a possibility envisaged in the Bergen meeting was not necessary, since partners felt that  project activities could be adequately carried out by e-mail.

# Summary of the main results achieved

The Young-Lit project is part of the Culture 2000 Programme which deals with the promotion of books and reading, aimed at the target group of so-called young adults, that is, young people between the ages of 14 and 18.

Aim

Through their activities partners aimed at creating a European communication network, which, through the direct participation of young people and schools, the involvement of the operators in the field, the institutions and the authors, provides young adults (14/18) with an instrument that allows them to exchange information about national publications, in order to get to know authors from their own and other countries.

The project’s aim was, in fact, promoting, through young people’s suggestions, the translations and publication of targeted titles.

To achieve this aim the main actions of the project were:

- Creation of four publishing workshops in four European libraries connected with one another.

- Each workshop aimed to establish a link with young people aged 14-18 in its country in order to open an on-line editorial office providing materials and works for a literary e-magazine entirely designed and written by young adults, in a website that would be up-dated, with the direct contribution and involvement of young visitors.

- Each partner country set up a local editorial office involving several schools and students

- The network of local editorial offices was co-ordinated by the project leader, the Municipality of Bologna, and by its Italian partner "Associazione Pagine". The main editorial office is in Bologna, at the prestigious location of the Sala Borsa Multimedia Library

- Following instructions on the website, the students acted as journalists reviewing books, interviewing authors, librarians and booksellers, and creating their own book lists, even working from the library, their classes or from home, keeping in constant touch with their editorial office.

- The books to be reviewed and illustrated were chosen, during the first period of the project, by the partners, each selecting about 50 titles. In future the book lists to be reviewed and illustrated can be added to based on the requests of the young people involved and other visitors to the site.

Objectives

- Creation and implementation of a “Young-LIT” e-magazine, including reviews and illustrations of books read, written by young people and with the contribution of art students.

- Setting up of a website (www.youg-lit.net) that in the long term, should become a reference point for young adult readers, for publishers, libraries, authors and booksellers throughout Europe, extending relations to other countries.

- Fostering discussion among students, promoting reading and creating a direct relationship with the best loved authors, who in a way, become, on the pages of the magazine, examples of creative writing.

- Allowing young people from different countries involved to suggest and get to know the authors of their own countries as well as to express their opinions on well known foreign authors.

- Project dissemination at a local, national and European level through Internet, and with appropriate links from civic networks, publishers' sites, educational sites and using networks of libraries - another good dissemination tool.

All the project objectives were achieved by the Young-LIT project,  by involving a high number of students, teachers and librarians and the most interesting result is certainly the students’ enthusiasm, their will to participate. Most of them asked to take part in next year’s workshops, and a number of classes that were not involved this year asked to have a workshop next time. All teachers appreciated the initiative which strongly fostered book reading for young people, and provided an addition to their curricula. Many schools stated their intention to repeat the experience next year with a larger number of classes.

Some of the students did not use the computer much before the project, and now are more aware of how it can be used.

In Ronneby, one boy who took part in the project had never read a whole book before, since he has a reading disability. For the project he  read and wrote about a novel and his effort is really the biggest of them all and now he is reading his second book.

The main aim of the project was to understand what young people like to read, and comparing their experiences in four different European countries confirmed what partners already suspected at the beginning of the project.The analysis of young adults' books was enclosed on purpose, as it was considered that a European comparison between young readers would provide very interesting results.

In fact, the reading material proposed as the focus of the research, young adults' books - which in Italy are published in specific series, while this is less so in the other countries - are not appreciated by young people who, in the age group considered by the project, read extremely different things, unspecific ones and certainly adults' books.. As a result of the project, the books being proposed were generally accepted positively in partner countries, while in Italy they were disputed, attesting the fact that the Italian publishing offer lags behind vis-à-vis the rest of Europe. So, books proposed in the UK, for example, which included many titles of adults' classics, would have been much more appreciated by Italian students, and this emerged clearly through the distribution of these books after the second meeting, which was quite successful.

This criticism has to be addressed especially by Italian publishing houses that tend to apply an outdated model no longer followed in other European countries, and it can be considered the most relevant result of the project research: stressing how the opinion of Italian teenagers essentially corresponds to that of their Norwegian, Swedish, British peers.

When left free to chose from the list, it was interesting to see that multiple reviews for particular titles were submitted. Perhaps this is due to word of mouth recommendations between the participants in the project.  It was also interesting to note that many of the reviews were submitted stating that they chose to read a particular title because of its appealing cover. This may not be the way in which books should be selected, but it does provide interesting information for publishers about what appeals to young people and how they should look at marketing the titles aimed at that age group.

The overall feeling is that between the age of 14-18, young people find alternative means of entertainment, television, computer games, socializing etc. and reading does not necessarily stop but transfers to newspapers and magazines as a preference. Those young people who enjoy reading and are keen readers use this time to experiment more with adult fiction, as it is perceived to have more credibility than the fiction written specifically for them.

Hopefully this project gives them a motivation to read more of this material before moving on to adult fiction.

Even if they are not inclined to read, young people 14-18 begin to form opinions and like those opinions to be heard.  The young-LIT website provides a forum for these opinions and at the same time uses this enthusiasm for criticism to steer them into reading more of the fiction written specifically for them.

Finally, it is very important that publishers become aware of this project. They are the link between readers and writers and, if the statistics are anything to go by, are not particularly successful in engaging with this audience. Young-Lit has produced a wealth of evidence, debate and written work that should enable the publishing industry to produce better books, responding to young people’s needs more closely and marketing them more positively. The result, it is hoped, will be an increase in reading among young people. Young-Lit has made a tentative but significant step forward toward a different future for young people’s literature.

Statistics of the project in Bologna

- 8 high schools joined the project in Bologna (Liceo Fermi, Liceo Righi, Liceo Sabin, Liceo Laura Bassi, Istituto comprensivo di istruzione superiore Crescenzi-Pacinotti, Istituto Aldini Valeriani Sirani, Istituto Rubiani, Istituto d’arte di Bologna) for the part of the project regarding the reviews, articles and creative writing, with a total of 10 participating classes. Several art colleges and schools joined from Bologna and Milan (Accademia d’Arte di Bologna, Istituto Rubiani, Istituto Superiore di disegno Anatomico, Istituto europeo di design di Milano, Istituto d’arte di Bologna) for the illustration part of the project.

- About 200 students were involved in the project in the Municipality of Bologna, working on reviews and articles, while about 100 illustrations were collected.

- Bologna chose 50 books for review and illustration.

Statistics of the project in the other partner countries

Bergen

- 3 local high schools and students already involved in an another literary project.

- The Art Academy in Bergen was contacted for illustrations

- Bergen chose 45 books for review and illustration.

Milton Keynes

- 2 schools were selected (Denbigh and Lord Grey schools)

- 80 pupils took part in the project.

- Milton Keynes chose 50 books for review and illustration.

Ronneby

- 4 schools were involved (Bräkne Hoby skola, Kallingeskolan, Snäckebacksskolan, Knut Hahnskolan)

- In the secondary school Knut Hahnskolan a whole class of art students was involved in illustrating books for the project.

- 78 pupils took part in the project.

- Ronneby chose 48 books for review and illustration.

The main product created within the project is an Internet Web site,

Address

www.young.-lit.net

# Description of major obstacles encountered and how they were overcome

There were no particular major obstacles in the implementation of the project. The planning was exceptionally thorough by all the partners. Partners did not specifically deviated from the original work plan, except sometimes by adding additional elements rather than removing any intended piece of work.

The obstacles encountered have already been mentioned in the workpackges description. Some of them are common to all the partners since Young-LIT is a project developed with students’ and schools’ involvement and so tightly linked to their time and school system (holiday, exams, homework, etc.), others are specific for each country.

Sometimes it was very difficult to convince teachers that it was important to participate in the project. However, once teachers agreed to participate, they easily recognised the importance of the work, as the feedback from the project shows (teachers and students asking to have workshops for next year).

This was specially true for Milton Keynes, fairly typical of any school-based project in the UK that involves extra curricular work. The UK National Curriculum is a very well defined set of work and it can be burdensome for teachers to achieve this, let alone consider anything additional. However, it is projects like Young-Lit that are so important in these circumstances. They offer an opportunity to stretch young people beyond the bounds of the curriculum and introduce them into an entirely new way of thinking, doing and learning.

Other obstacles were encountered in the collection of materials, that was delayed by others students engagements for the end of the school year.

There are also two other minor obstacles that have in part already been mentioned.

The first is a language problem. Since some of the participants in the local co-ordination teams did not speak English partners had to always use a translators, and this sometimes created misunderstandings and delays in the process, although these were easily overcome.

Another small problem was the differences in the four country in the use of computers in schools. While Scandinavian countries and in the UK are a little further ahead with having computers in schools and that affected the work, in Italy the situation seems to be not so good. In the other partner countries almost every classroom is equipped with one or more workstations, and teachers use it directly as a teaching tool.

In Italian schools, literature teachers usually do not use the computer which is located in a specific classroom, which students can access only according to a very strict agenda which is set once and for all at the start of the school year.

The situation is not the same in all schools and varies depending on the type of school involved: while the two "licei scientifici" were not well equipped with a computer classroom, the two technical institutes were fully equipped with computer classrooms, while the arts school did not have adequate IT provisions.

This situation partly limited the use of LUVIT in Italian workshops rather than in the other countries, although it only slightly delayed the collection of materials, as students often sent materials directly from their personal PC.

# Final remarks and future prosecution

As envisaged in the project work plan, with the public launch of the Young-LIT website, the project shifted from the local to the national level for each editorial team, and became transnational for the four editorial teams. Therefore all workshop activities had to be concluded in order to start new virtual ones. From this time onward, the editorial team no longer had to look for the schools intending to participate, as the schools themselves contacted the team, having visited the project website.

The working groups which followed the workshops in all the four European countries set up an editorial staff which, from the formal end of the project and for the entire summer up to the re-opening of the schools in September will continue to be responsible for running the web site. The workshops were closed at the end of the school term; so partners will have to wait for the summer months to see whether the site can draw the attention of young people independently from schools and have a life of its own; whether it gets to be isolated in its country of origin or not.

The first part of this dissemination activities was concluded with the final event and other advertising activities. Each central library had to further develop this dissemination activity, contacting all the major national libraries and informing all high schools, libraries, publishing houses, authors, of the Young-LIT site so that they can browse and “leaf through” it, so increasing the number of website visitors.

So in all the four countries involved in September, when the schools return from their Summer Holidays, other dissemination activities will be done to achieve the important result to let people know that the website exists and what it is for. Partners’ aim is to disseminate the project first at a national level, hoping that at least every school in the partner country becomes aware of the project and should be able to submit literature reviews to the site, but also at European level using all available civic networks, publishers’ and educational sites, and networks of libraries too.

If from September onward schools are again involved in a reading project as an effect of the dissemination activities, it will be not only at local, but also at national and European level, and this does obviously imply a workload for the editorial staff, whose survival will depend on two factors:

- Human resources availability in each country

- Fund raising activities at local, national and international level

All partners confirmed their interest in continuing the Young-LIT project with their own internal resources (work to be done by the editorial office), but they all agreed that, on the basis of the possible exploitation of the project at a national level, it will be necessary to evaluate the total effort required.

In any case, the problem of how to continue the work will have to be faced in September, especially if the number of young people visiting the website increases at  national and European level

Each partner will promote the site and will try to find funds and sponsors, since the survival of the project depends mainly on the possibility to finance activities both at local/national level for the workshops and at European level for extending the Young-LIT network to other countries and adding new features and contents to the website.

Furthermore, in order to update each other on activities developed in each editorial office and to assess possible further projects, the partners have decided to set up a discussion forum between the local co-ordination teams. To this aim, a mailing list was circulated within the consortium containing the contact addresses of all the people involved in the Young-LIT project.

The first deadline chosen for updating each other about the editorial offices activities was the first week of July.

The second deadline was set for mid September, after the summer holidays, to evaluate the dissemination activities feedback and discuss the website exploitation.

Final remarks

All project partners feel that it has been interesting to work with other European countries on a literature project, when each country has a different publishing industry and education system. It has been valuable to be able to exchange experiences and ways of thinking with the partners.

These differences have meant that the project has gone in different directions in each country, while always working towards a common goal. It ss an important result to have enabled young people to communicate and exchange ideas with their peers in other countries, to give them an insight into to how the world approaches similar ideas differently. The schools and the students have found the project useful not only as a teaching tool, but also from a citizenship point of view, teachers and pupils are now more aware about the European Union and learning about other cultures is an important part of the students’ curriculum so the project has had an interesting offshoot.

All the people involved in the local teams, librarians, local schools, teachers and, most importantly, young people, have benefited enormously as a result of this project.

Transnational working can be complex, intricate and time consuming. However, the sharing of best practices, different work methods, philosophies and cultural perspectives that has been achieved could never have produced so rich an experience at a purely national level.

The young people participating in the project can look back with a real sense of pride and achievement on their results, knowing that the excellent work they have produced is being considered and enjoyed by young people in other countries.

However, the results have been tangible and real the aim now is to sustain these benefits by extending the project throughout the partner countries and by disseminating the project results very widely within the European Union.

Young-LIT has produced a wealth of evidence, debate and written work that should enable the publishing industry to produce better books, fulfilling the aspirations of young people more closely and that are marketed more positively. The result, it is hoped, will be an increase in reading by young people. Young-Lit has made a tentative but significant step forward toward this different future for young people’s literature.